# Native iOS / React Native Migration — Effort Estimate

Document purpose: Assess the level of effort to migrate the current Feedback (Momentum) codebase and data structure into a fully native iOS experience built with React Native.

Last updated: June 26, 2026

# Executive Summary

This is a medium-to-large rewrite, not a conversion. The backend and data model are largely reusable, but the iOS client UI and device integrations would need to be rebuilt.

Estimated effort ranges (one experienced iOS/React Native engineer, part-time QA):

| Scope | Timeline |
| --- | --- |
| Prototype / thin native shell | 2–4 weeks |
| Usable MVP (feed, auth, profiles, clip viewing, basic upload) | 6–10 weeks |
| Feature-parity iOS app | 12–20+ weeks |
| Swift/SwiftUI rewrite (not React Native) | 16–30+ weeks |

# Current Architecture

React 19 web app (Vite) with react-router — ~37 pages, 120+ components

Capacitor 7 iOS shell wrapping dist/ (or remote Worker URL) — not a native UI layer

Cloudflare Worker API (Hono) with D1 database, R2 storage, Cloudflare Stream

Session-cookie auth via @getmocha/users-service

Native bridges today: push notifications, filesystem, gallery save (Capacitor plugins)

Heavy browser APIs: MediaRecorder, getUserMedia, IndexedDB upload outbox, canvas thumbnails

# What Is Reusable

These layers can largely stay as-is or be shared with minimal changes:

Cloudflare Worker API and all /api/* endpoints

D1 schema and 60+ SQL migrations (clips, users, shows, notifications, gamification, etc.)

R2 / Stream video pipeline and multipart upload sessions

Third-party integrations: JamBase, Ticketmaster, Stripe, AudD/ACRCloud, YouTube

Shared TypeScript business logic in src/shared/ (show matching, content feed, types)

API contracts and data shapes consumed by the client

# What Must Be Rewritten

All UI: DOM components → React Native (View, Text, FlatList, etc.)

Routing: react-router → React Navigation (stack, tabs, deep links)

Styling: Tailwind/CSS → StyleSheet or NativeWind (no direct transfer)

Video capture & upload: UploadClip.tsx (~3,300 lines), QuickCaptureOverlay, camera zoom, thumbnails

Upload outbox: IndexedDB + in-memory blob registry → AsyncStorage/SQLite + filesystem

Auth/OAuth: cookie sessions and /auth/callback → native deep links + secure token storage

Push notifications: Capacitor plugin → APNs + React Native push library

Photo library, camera, mic permissions → native modules (expo-camera, react-native-vision-camera, etc.)

Background upload: scaffolded in native-bridge.ts but not fully wired — needs URLSession implementation

Live features: WebSocket chat, live broadcast, polls — native equivalents

Admin/moderation dashboards, analytics charts (recharts) — lower priority, significant UI work

# High-Risk / High-Effort Areas

| Area | Why It's Hard | Rough Effort |
| --- | --- | --- |
| Clip capture & upload | MediaRecorder, blob lifecycle, offline queue, multipart resume, song ID, show matching | 4–8 weeks |
| Auth & sessions | Cookie-based Mocha auth, OAuth redirect flow, password reset deep links | 1–2 weeks |
| Video playback feed | HLS via hls.js today; need expo-av or react-native-video + prefetch/limiter logic | 2–3 weeks |
| Push & notifications | APNs registration, badge counts, in-app notification panel | 1–2 weeks |
| Discover & search | JamBase geo search, trending carousels, infinite scroll grids | 2–4 weeks |
| Admin / superadmin | Moderation panels, role management, analytics — web-only tooling today | 3–5 weeks (optional) |

# Recommended Phased Approach

Keep the existing Worker API and shared logic. Build a React Native iOS app alongside the web app.

Phase 1 — Foundation (2–3 weeks): RN project scaffold, API client, auth, navigation shell

Phase 2 — Core experience (3–4 weeks): Home feed, clip playback, profiles, saved/liked clips

Phase 3 — Capture & upload (4–6 weeks): Camera, upload queue, offline outbox, gallery save

Phase 4 — Discovery (2–3 weeks): Discover, nearby/tonight shows, artist/venue pages

Phase 5 — Engagement (2–3 weeks): Push, notifications, show marks, gamification/points

Phase 6 — Parity (ongoing): Live features, admin, sponsor/ambassador dashboards, analytics

# Alternatives Considered

Stay on Capacitor: lowest effort; current path. Limitations: WebView performance, background upload gaps.

Capacitor + native plugins for capture/upload only: hybrid — keep web UI, replace hardest native pieces.

React Native (recommended for 'native React iOS'): best balance of code reuse (shared TS logic) and native UX.

Swift/SwiftUI: maximum native feel; zero UI reuse; longest timeline unless team is iOS-first.

# Key Codebase References

| Path | Role |
| --- | --- |
| src/react-app/App.tsx | 37 routes, providers, native bootstrap |
| src/react-app/pages/UploadClip.tsx | Largest client file — capture, tagging, upload enqueue |
| src/react-app/contexts/ClipUploadQueueContext.tsx | FIFO upload queue, IDB recovery, retry logic |
| src/react-app/lib/native-bridge.ts | Capacitor push, filesystem, gallery save |
| src/react-app/lib/apiFetch.ts | Session-cookie API client |
| src/worker/index.ts | Main Worker API surface |
| migrations/ | D1 schema (60+ migrations) |
| capacitor.config.ts | Current iOS shell config |

See also: docs/upload-flow-developer-summary.docx (upload pipeline), docs/upload-outbox-build.md (outbox architecture).

Feedback (Momentum) — Native iOS Effort Estimate